## Client Feedback Log
Sprint | Date | Related Epic | Feedback | Priority | Assigned To | Status / Outcome
Sprint 1 | 29-Jul-2026 | Authentication & Security | Ensure user login uses strong password hashing and stateless auth so the API scales without server-side sessions. | High | Dhruv | Implemented - JWT auth + BCrypt hashing (JwtAuthFilter, SecurityConfig)
Sprint 2 | 02-Aug-2026 | Payment Processing | Need support for multiple payment methods, not just bank transfer. | Medium | Dhruv | Implemented - PaymentMethod enum added to Payment model
Sprint 2 | 02-Aug-2026 | Payment Processing | Sensitive account details must be protected at rest, not just in transit. | High | Anusree | Implemented - encryption added for account details in payment service
Sprint 3 | 03-Aug-2026 | DevOps & Infrastructure | Application should be easy to run consistently across environments for demos and grading. | Medium | Dhruv | Implemented - Dockerfile (backend/frontend) + docker-compose.yml
Sprint 3 | 03-Aug-2026 | Testing & Quality Assurance | Core auth and payment logic needs automated test coverage before further features are layered on top. | High | Anusree | Implemented - unit tests for auth and payment service
Sprint 4 | 04-Aug-2026 | Payment Processing | Payment history must explicitly show failed transactions and handle rollback cleanly, with the money visibly returned. | Critical | Dhruv | Implemented - deterministic failure simulation + automatic refund/rollback + audit history logging
Sprint 4 | 04-Aug-2026 | Payment Processing | Users should be able to search/filter their payment history by status, amount, and date. | Medium | Dhruv | Implemented - GET /api/payments/search endpoint with status/amount/date filters
Sprint 4 | 04-Aug-2026 | Security & Authentication | Users should be able to change their own password without contacting support. | Medium | Anusree | Implemented - isolated password-change feature (reverted once, re-added cleanly) via AccountController/PasswordService
Sprint 5 | 05-Aug-2026 | DevOps & Quality | Project needs clear agile documentation (vision, epics, sprint allocation) for client/stakeholder visibility. | Medium | Dhruv | Implemented - agile sprint documentation and architectural specs added
Sprint 5 | 05-Aug-2026 | User Experience & Frontend | Payment list page should expose the new amount/date range filters directly in the UI, not just via API. | Medium | Chaitanya | Implemented - amount and date range filters added to Payment List page

## Decision Log
ID | Sprint | Date | Decision | Reason | Impact | Owner
DEC-01 | Sprint 1 | 29-Jul-2026 | Use Spring Boot and React/Vite | Aligns with team expertise and project requirements | Determines the complete tech stack | Dhruv
DEC-02 | Sprint 1 | 29-Jul-2026 | Implement JWT for stateless auth | Better scaling; no session state required on the API | Requires custom JwtAuthFilter | Dhruv
DEC-03 | Sprint 2 | 02-Aug-2026 | Simulate external payment gateways instead of real integration | Scope restriction; real payment gateway integration not required for assessment | Created internal state-transition simulation in PaymentService | Anusree
DEC-04 | Sprint 4 | 04-Aug-2026 | Rename project package/branding from FlowPay to PayFlow | Standardize naming across team after parallel branch work created inconsistent package names | Required merging unrelated git histories (--allow-unrelated-histories) and removing leftover com.flowpay files | Dhruv
DEC-05 | Sprint 4 | 04-Aug-2026 | Make every 3rd transaction fail deterministically (instead of random) | Random success/failure was not reliably demonstrable/testable for the client demo | Added AtomicLong transactionCounter to PaymentService for repeatable, testable failure simulation | Dhruv
DEC-06 | Sprint 4 | 04-Aug-2026 | Debit funds upfront and auto-refund on failure (rollback) instead of retry | Client required money to never be stuck; retry added complexity without guaranteeing fund safety | Retry feature fully removed; rollback/refund + 3-stage audit history (initiated/refunded/completed) added instead | Dhruv
DEC-07 | Sprint 4 | 04-Aug-2026 | Isolate password-change feature into its own branch/commit after a revert | First attempt was reverted due to it being bundled with unrelated changes; re-added cleanly on its own | Cleaner git history; AccountController/PasswordService added as a standalone, reviewable feature | Anusree
DEC-08 | Sprint 5 | 05-Aug-2026 | Use GitHub Actions (not Jenkins) for CI/CD | GitHub-native, zero infra to host/maintain, sufficient for build+test+docker-build at this project scale | ci.yml covers build-backend, build-frontend, and docker-build jobs; no self-hosted CI server needed | Dhruv