## Meeting Minutes
Meeting ID | Type | Date | Time | Attendees | Agenda | Decisions | Action Items
M-01 | Client Kickoff | 29-Jul-2026 | 10:00 AM - 11:30 AM | Client, Dhruv, Anusree, Chaitanya | Project goals, requirement gathering, timeline | Focus on payment lifecycle, REST API, React frontend. Confirmed sprints. | Dhruv to setup repo; Chaitanya to init Vite; Anusree to design DB schema.
M-02 | Sprint 1 Planning | 29-Jul-2026 | 09:30 AM - 10:30 AM | Dhruv, Anusree, Chaitanya | Sprint 1 Backlog selection | Commit to frontend setup, Spring Security (JWT), and basic React routing. | Anusree: AuthController; Chaitanya: App.jsx routers.
M-03 | Architecture Discussion | 01-Aug-2026 | 02:00 PM - 02:45 PM | Dhruv, Anusree | AES Encryption & JWT Strategy | Implement custom JwtAuthFilter and AesEncryptionUtil for sensitive data. | Dhruv to write AesEncryptionUtil.
M-04 | Sprint 1 Review | 02-Aug-2026 | 03:00 PM - 04:00 PM | Client, Dhruv, Anusree, Chaitanya | Demo Auth & Infra | Approved infrastructure. Client requested explicit hashing for user login. | Added to Sprint 2 backlog.
M-05 | Sprint 3 Planning | 03-Aug-2026 | 09:30 AM - 10:30 AM | Dhruv, Anusree, Chaitanya | Dockerization & Deploy | Focus heavily on docker-compose for consistent environments. | Dhruv to implement docker-compose.yml